## Slide 1: Change Management Template March 18, 2015

## Slide 2: What is Change Enablement?
Change Enablement is the process of changing individual behaviors to increase readiness and productivity when implementing a process, technology or organizational change.

## Slide 3: Our Conversation Today…
IS about:
A practical approach to orchestrating change
What people need in order to be able to change
Laying foundation for a successful transition
IS NOT about:
Change theory
An endorsement of any one of the hundreds of change models out there (we’re change model agnostic)
Notes: There are lots of change models out there. Some are really expensive. Some are really complicated. Most are process models. This is about a practical way to get to the new way. This is about putting theory into practice.

## Slide 4: Agenda – Note change based on final outcome
Plan
  Define Success
  Manage Expectations
  Establish Controls
  Define Roles
Discover
  Review Experiences
  Audience Analysis
  Impact Analysis
  Identify Barriers
Build
  Establish Message
  Build Communication & Marketing Plan
  Build Training Plan
  Identify Action Items

## Slide 5: Change Management Overview

## Slide 6: Change Management
  Your implementation can only be successful if it rolls out well
    End user adoption
    Understand the need
  Maximize your investment in technology and business process
  Organizations will only change if the individuals change first
Notes: Implementation will only be successful if:
Stakeholder involvement
Executive Management support
Line level manager coaching and readiness

## Slide 7: When To Start Change Enablement
Notes: The premise of this slide is to talk about the importance of getting CE engaged in the process as early as possible. It gets at the point of when people have started CE activities in the past for initiatives and when they would do it in the future – based on what they learned

## Slide 8
Copyright Prosci 2009
Change Implementation Related to Objectives
Notes: This talks about how research shows that when CE is integrated in the project at earlier stages, the likelihood that project objectives will be met increases dramatically.

## Slide 9: Change Enablement Effectiveness
Notes: This represents the likelihood that project objectives will be met if you have a complete and comprehensive change management plan. The better the program, the higher the percentage of objectives are met.
“Of the 107 research participants who reported having excellent change management effectiveness, 95% met or exceeded project objectives.”
“Participants with the highest level of change management effectiveness were nearly 6X more likely to meet or exceed project objectives.”

## Slide 10: Greatest contributors to success
Active and visible executive sponsorship
Frequent and open communications
Structured change management approach
Dedicated resources for change management
Employee participation
In all five Prosci CE studies, sponsorship was #1
How effective are your sponsors?
Notes:   Even if you like change, even if it’s a “good” change being made—change organically produces some degree of stress in humans
  People perceive change as a threat
    We need to adjust the perception to show where the threat is not actually real
    Real risks need to be identified and managed
Common phrases you might hear: I’m already overworked. HR keeps trying new systems to see what sticks. I don’t have the time to learn a new system.

## Slide 11: When we don’t manage change effectively, we can expect:
Lower productivity
Passive and Active resistance
Turnover of valued employees
Disinterest in the current or future state
Arguing about the need for change
Changes not fully implemented
People finding work-arounds
People revert to the old way of doing things
The change being totally scrapped
Divides are created between ‘us’ and ‘them’
Notes:   Even if you like change, even if it’s a “good” change being made—change organically produces some degree of stress in humans
  People perceive change as a threat
    We need to adjust the perception to show where the threat is not actually real
    Real risks need to be identified and managed
Common phrases you might hear: I’m already overworked. HR keeps trying new systems to see what sticks. I don’t have the time to learn a new system.

## Slide 12: Change Management
  Change produces some degree of stress in humans
  Some people perceive change as a threat
Notes:   Even if you like change, even if it’s a “good” change being made—change organically produces some degree of stress in humans
  People perceive change as a threat
    We need to adjust the perception to show where the threat is not actually real
    Real risks need to be identified and managed
Common phrases you might hear: I’m already overworked. HR keeps trying new systems to see what sticks. I don’t have the time to learn a new system.

## Slide 13: Change Management
  People change at their own pace
  You only have ONE chance at making a first impression
Notes:   Even if you like change, even if it’s a “good” change being made—change organically produces some degree of stress in humans
  People perceive change as a threat
    We need to adjust the perception to show where the threat is not actually real
    Real risks need to be identified and managed
Common phrases you might hear: I’m already overworked. HR keeps trying new systems to see what sticks. I don’t have the time to learn a new system.

## Slide 14: Four Fundamental Needs
KNOWLEDGE
MOTIVATION
STRUCTURE
SKILLS
BASICS
S
S
M
K

## Slide 15: Four Fundamental Needs
What does the change involve
When
Interim steps
Who is responsible for what
New policies
Where to find ongoing access to training
KNOWLEDGE
K
K
Your own footer
Covers all the information people need to know in order to change:

## Slide 16: Four Fundamental Needs
New technologies
New processes and procedures
SKILLS
S
S
Covers all the things people need to be able to do in order to change:

## Slide 17: Four Fundamental Needs
Why this change is being made
What benefits can be expected
Why and how the change matters to the organization, culture, mission, etc.
MOTIVATION
M
M
Your own footer
Refers to what people need to believe in order to change:

## Slide 18: Four Fundamental Needs
Success criteria and reporting
Program expectations
Management oversight & accountability
STRUCTURE
Your own footer
S
S
Encompasses all the elements that ensure change happens, and reports on progress:

## Slide 19: Typical Ways to Meet Needs
KNOWLEDGE:
Communication
Documentation
Schedules & calendars
Memos, email
Meetings, teleconferences
SKILLS:
Training & meetings
Practice & feedback
Checklists
Job aids
Coaches
MOTIVATION:
Organizational “Story”
Marketing campaigns
Leader advocates
Positive reinforcement
Accomplishment celebration
STRUCTURE:
Active Sponsorship & Support
Progress reports & follow-up
Feedback mechanisms
Ownership accountability
Advocacy program
Notes: Advocacy program is the structure to create “in-business” experts that help support after go-live.
Leader advocates are the primary “cheerleader” and main face of the program.

## Slide 20: Change Strategy

## Slide 21: Components of a Change Strategy
Discover
Review Experiences
Impact Analysis Review
Build
Build Comm & Marketing
Build Training
Identify Barriers
Identify Action Items
Establish Message
Plan
Define Success
Manage Expectations
Establish Controls
Define Roles
Audience Analysis
Notes: Note – need to flip identify barriers and impact analysis flow and on subsequent slides.
Also, build communication & Marketing put together, move up build training and add action items.

## Slide 22: Plan

## Slide 23: Define Success
Discover
Review Experiences
Impact Analysis Review
Build
Build Comm & Marketing
Build Training
Identify Barriers
Identify Action Items
Establish Message
Plan
Define Success
Manage Expectations
Establish Controls
Define Roles
Audience Analysis
Plan your success metrics to confirm that you configure the system to allow access the data you need later.
System decisions must ultimately reflect how you hope to impact your organization

## Slide 24: Measuring Your Success
  What metrics will your organization expect to see?
What metrics can be added or adjusted to best show the impact you have made?
  What do you plan to accomplish with the initiative?
Response:
Response:
Response:
Notes:     *Tip- Helping your End Users understand that they are successful is an important and often overlooked element of Success Measurement

## Slide 25: Measuring Your Success
  Are there data points that will need to be collected outside of the system?
Response:
  How will people know if they are using the system successfully?
Response:
Notes:     *Tip- Helping your End Users understand that they are successful is an important and often overlooked element of Success Measurement

## Slide 26: Success Metrics
Success Metric | Impact Measured | How this will be collected | Audience | Frequency

## Slide 27: Setting Expectations
Discover
Review Experiences
Impact Analysis Review
Build
Build Comm & Marketing
Build Training
Identify Barriers
Identify Action Items
Establish Message
Plan
Define Success
Manage Expectations
Establish Controls
Define Roles
Audience Analysis
Determine short and long term goals to confirm you are meeting your roll-out plan
Roll-out plans can be broken out in any time frame you prefer
  We recommend
30
90
180
365
Notes:     Tip: Include your 30, 90, 180, and 365 expectations in your communication to Executives, HR Leadership, and OU Leads to increase alignment.

## Slide 28: Expectations and Examples – include the explanations in the previous slide
30
Roll-out
180
Tactical
365
Strategic
90
Roll-out
Notes: 6 months- Expect to be able to see changes in your organization that meet tactical goals
1 year-Expect to begin to see the impact from your roll out on employee empowerment and engagement around the year mark

## Slide 29: 30, 90, 180, 365 Day Expectations
Timeframe | What will be measured | How this will be collected | Audience | Method of Delivery
Example- 30 Day | Number of users who have logged into the system | System reports | HR Leadership | Excel report
Example

## Slide 30: Establish Controls
Plan
Build Training
Build Comm & Marketing
Establish Message
Build
Identify Barriers
Audience Analysis
Review Experiences
Discover
Define Roles
Establish Controls
Manage Expectations
Define Success
Impact Analysis Review
Identify Action Items
Develop a Change Management project plan
Determine team structure to deliver change management
Understand post go-live process to ensure continued reinforcement and change process
Establish feedback channels
Notes: Add potential changes for including governance type discussion and the 4X release cycle.

## Slide 31: Roles Needed to Execute Change
Discover
Review Experiences
Build
Build Comm & Marketing
Impact Analysis Review
Build Training
Establish Message
Plan
Define Success
Manage Expectations
Establish Controls
Define Roles
Audience Analysis
Identify Barriers
Identify Action Items
Sponsors
Make Decision to Change
Change Advocates
Change Leader
Change Targets
Those effected by the change
Fund Change
Confirm Change and Support it
Communications
Marketing
Trainers
Influencers

## Slide 32: Change Roles & Action Plan
Change Role | Expectations Of Role | Organizational Unit | Name | Action Items
Authorizing Sponsor |  |  |  | 
Reinforcing Sponsor |  |  |  | 
Change Advocates |  |  |  | 

## Slide 33: Discover

## Slide 34: Review Experiences
Discover
Review Experiences
Build
Build Comm & Marketing
Impact Analysis Review
Build Training
Establish Message
Plan
Define Success
Manage Expectations
Establish Controls
Define Roles
Audience Analysis
Identify Barriers
Identify Action Items
What roll outs have you experienced recently?
What worked well?
  What do you want to duplicate?
What did not work?
  What do you want to avoid?

## Slide 35: Audience Analysis
Discover
Review Experiences
Build
Build Comm & Marketing
Impact Analysis Review
Build Training
Establish Message
Plan
Define Success
Manage Expectations
Establish Controls
Define Roles
Audience Analysis
Identify Barriers
Identify Action Items
Groups to consider
  Executives
  Organizational Unit Leads
  Unions
  IT
  Human Resources
  End Users
  External, e.g. Partners and Vendors
Who is impacted by the change?

## Slide 36: Audience and Impact Analysis
  How are they impacted by change?
  What motivates them?
  Who is impacted by the change?
Notes: Take-away

## Slide 37: Impact Analysis
  What resistance might they have about this change?
  What is source of resistance (emotional, cognitive, behavioral)?
  Who influences these people?

## Slide 38: Impact Analysis
  How can you leverage influencers to manage resistors?
  What do they need to KNOW relative to the change?
  What do they need to DO relative to the change?

## Slide 39: Impact Assessment

## Slide 40: Identify Barriers
Discover
Review Experiences
Identify Barriers
Build
Build Comm & Marketing
Build Training
Establish Message
Plan
Define Success
Manage Expectations
Establish Controls
Define Roles
Audience Analysis
Impact Analysis Review
Identify Action Items
What are there barriers which will inhibit change?
Political
Geographical
Financial
Cultural
Technical
Informational
Time Restriction
Political
Financial
Technical

## Slide 41: Barriers Assessment
Barrier | Type of Barrier | How it Impacts Change | Plan to Overcome
Example

## Slide 42: Build

## Slide 43: Build Communication
Discover
Review Experiences
Build
Build Comm & Marketing
Build Training
Impact Analysis Review
Establish Message
Plan
Define Success
Manage Expectations
Establish Controls
Define Roles
Audience Analysis
Identify Barriers
Identify Action Items
To begin creating your message, start by building your ‘elevator pitch’
This gives you
  Building blocks to build out future communications
  Consistency, while allowing each person to develop their message on their own
Notes:   This method of ‘just in time’ delivery will make the message you deliver better resonate

## Slide 44: Establish Message: Brainstorming
  Why did your organization decide to make this change?
Brainstorming:
Concise (Refined) Message:
Notes: Alternate facilitation – if participants in workshop exceed 10 participants, you can conduct a group exercise breaking in to groups of 3-5 people. Have them create their own individual brainstorm and message and then debrief as a larger group. Final output is based on the group input.
Add notes on prompting questions during the brainstorm session.

## Slide 45: Build Communication
Discover
Review Experiences
Build
Build Comm & Marketing
Impact Analysis Review
Build Training
Establish Message
Plan
Define Success
Manage Expectations
Establish Controls
Define Roles
Audience Analysis
Identify Barriers
Identify Action Items
Deliver the right amount of data to your audience at the point they need the information
Notes:   This method of ‘just in time’ delivery will make the message you deliver better resonate

## Slide 46: Delivery of Materials
What we need from you,
How it effects you
What to do,
When to do it
Overall concept,
High level
Proximity to live date
Level of detail
Notes: Overall high level messaging- elevator pitch, by audience- benefits, what’s in it for me, etc.
What we need from you and How it effects you
What to do, when to do it, examples

## Slide 47: Frequency of Message
Utilizing multiple methods to reach your audience assures that your message is heard
  Multiple deliveries are required for receiver recognition
  Reference- television commercials
    12 times
  Single method delivery
    Not effective
Notes:   Generally any single message will need to be delivered in multiple ways before the receiver of the message recognizes that they have heard the message
  For reference, think of television commercials- a viewer watches a commercial an average of 12 times before they realize they have seen the commercial before
  To reach your audience, using a single method such as email, may not be effective

## Slide 48: Getting Your Message Heard
In order to take the time to pay attention your message, the reader must have some reason to care
  Executives or direct line management
Notes: In order to take the time to pay attention your message, the reader must have some reason to care
  Where possible, have messages delivered from executives or direct line management of the individuals receiving the message
    Employees are far more likely to embrace programs where executives or their direct line management has shown support for the program

## Slide 49: Marketing Communication Ideas
Discover
Review Experiences
Identify Barriers
Build
Build Comm & Marketing
Build Training
Establish Message
Plan
Define Success
Manage Expectations
Establish Controls
Define Roles
Audience Analysis
Impact Analysis Review
Identify Action Items
What can you use to create a buzz about the change?
Options to consider
  Events
  Contests
  Campaigns
  Give-Aways
Notes:   This method of ‘just in time’ delivery will make the message you deliver better resonate

## Slide 50: Methods of Delivery
  How does your company communicate?
What methods are most effective and for whom?
What avenues do you have to deliver your message?
  Options to Consider:
  Team Meetings , Quarterly Addresses, HR BP Meetings, Newsletters, Intranet, Lunch and Learns, Posters, Table Tents, Email Signatures, WebEx

## Slide 51: Communication Plan
Audience | What will be communicated | Method of delivery | Timeline | Owner/ Author
Executives and Human Resources | Review of why we changed performance vendors, what the benefit of the new partnership will be, when the change will take place, and who will be impacted by the change | PPT at monthly meeting | 8 weeks before live | VP of HR
Example

## Slide 52: Finalize Your Communication Plan
Once you have added all messages to the tables provided, you may find it helpful to transfer the dates to a calendar or add them to your project plan
  This visual format tends to be more useful for better understanding deadlines
  You may find it helpful to start with a calendar and work backward to add it to your Communication Plan
Notes: Notes about calendaring and revision control.

## Slide 53: Build Training
Discover
Review Experiences
Build
Build Comm & Marketing
Impact Analysis Review
Build Training
Establish Message
Plan
Define Success
Manage Expectations
Establish Controls
Define Roles
Audience Analysis
Identify Barriers
Identify Action Items
How does your company learn?
Notes:   This method of ‘just in time’ delivery will make the message you deliver better resonate

## Slide 54: Training Delivery
  What methods of training are available?
Response:
  What methods are most effective and for whom?
Response:
  What training methods worked well in the past? Where can you improve?
Response:
Notes: These slides are helpful if the client is going live with the performance cloud and may not been necessary for the other clouds. May be more significant if there are any types of process changes in the system.

## Slide 55: Training
Outside of training on technology, are there new processes or procedures to be integrated into the training?
Response:
How will training be delivered after the initial roll-out?
Just in time training:
Training for new hires:

## Slide 56: Training Plan
Audience | What are the skills to be trained | Method of delivery | Timeline | Owner
Regional admins | Reporting | Online training in LMS | 3 days before live | Project Lead
Example

## Slide 57: Action Items
Notes: To be delivered in the final version of the presentation by the facilitator.

## Slide 58: Action Items
ID | Follow-up Item | Owner | Comments
1 |  |  | 
2 |  |  | 
3 |  |  | 
4 |  |  | 
5 |  |  | 
6 |  |  | 
Notes: This is to be completed by the facilitator after the session is over and should highlight standard items used in delivering the CE plan as well as any action items that came up in the workshop.

## Slide 59: Closing Thoughts
As long as you keep the needs of people at the heart of your plan, there are many ways to orchestrate successful and lasting change.